## TPSODL PSD OUTAGE
SL NO | VOLTAGE LEVEL | GSS/PSS NAME | CIRCLE NAME | DIVISION NAME | SUBDIVISION NAME | SECTION NAME | EQUIPMENT NAME | OUTAGE TYPE | OUTAGE SUB TYPE | WORK DESRIPTION | ISOLATION TYPE | AFFECTED CONSUMER | AFFECTED HT CONSUMER | AFFECTED AREA | PLANNED START DATE | PLANNED END DATE | DURATAION | BACKFEEDING PROVISION (Y/N)
1 | 33KV | SORADA | BHANJANAGAR | BNED | SORODA | SORODA | 33KV O/G HTC KARADABADI VILLAGE | PLANNED SHUTDOWN | PROJECT WORK | 33KV KARADABADI VILLAGE LC REQUIRED FOR REPLACEMENT OF OLD DAMGAED CONDUTPORS AND INSTALLATION OF INTERMEIDIATE POLE UNDER CAPEX-SCHEME AT KARADABADI VILLAGE | COMPLETE FROM BREAKER AND GOD OF GSS/PSS | 110 | 0 | KARDABADI VILLAGE | 2022-10-12 09:30 | 2022-10-12 13:30 | 4:00 | NO
2 | 33KV | BALIMELA | JEYPORE | MED | BALIMELA | BALIMELA | 33 KV O/G KORKUNDA | PLANNED SHUTDOWN | TREE TRIMMING WORK | 33KV O/G LC REQUIRED FOR TREE TRIMMING WORK IN BETWEEN BALIMELA TO KORKUNDA PSS AND AB SWITCH REPAIRED WORK AT KORKUNDA PSS. | COMPLETE FROM BREAKER AND GOD OF GSS/PSS | 20800 | 1 | KORKUNDA PSS, MV-27 PSS & HTC-SINGHASINI STONE CRUSHER | 2022-10-12 08:00 | 2022-10-12 12:00 | 4:00 | NOT REQUIRED
3 | 33KV | SORADA | BHANJANAGAR | BNED | SORODA | SORODA | 33KV O/G HTC KARADABADI VILLAGE | PLANNED SHUTDOWN | PROJECT WORK | 33KV KARADABADI VILLAGE LC REQUIRED FOR REPLACEMENT OF OLD DAMGAED CONDUTPORS AND INSTALLATION OF INTERMEIDIATE POLE UNDER CAPEX-SCHEME AT KARADABADI VILLAGE | COMPLETE FROM BREAKER AND GOD OF GSS/PSS | 110 | 0 | KARDABADI VILLAGE | 2022-10-13 09:30 | 2022-10-13 13:30 | 4:00 | NO
4 | 11KV | BALIMELA | JEYPORE | MED | BALIMELA | BALIMELA | 11KV SADASHIVPUR | PLANNED SHUTDOWN | ROUTINE MAINATENANACE | 11KV SADASHIV FEEDER LC REQUIRED FOR THE CONDUCTOR STRINGING WORK AT MV38 AS THE GROUND CLEARENCE VERY LOW. | COMPLETE FROM BREAKER AND GOD OF GSS/PSS | 1857 | 0 | KHILA GUDA, OLD BALIMELA,MV-38 RWSS,MV-36 RWSS,APANMELA,JABA GUDA RWSS,GOPAL PUR,SOMNATH PUR,KANDEL,ALAHGUDA,RANGAM GUDA,SARGI GUDA (WHOLE SADASHIVPUR FEEDER) | 2022-10-13 10:10 | 2022-10-13 14:00 | 3:50 | NOT REQUIRED